## Light
INFO310
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Start date: | 2025-03-16 |  |  |  |  | March | [20 empty] | April | [27 empty] | May
Scrolling increment: | 0 | time axis 2025-03-16 to 2025-05-23
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-03-16 to 2025-05-23
Project development
Milestone 1 | Milestone |  |  | 2025-04-14 | 1 | bar: 2025-04-14
Software Deliverable | Milestone |  |  | 2025-05-23 | 10 | bar: 2025-05-23
ERD Diagrams | Low Risk |  |  | 2025-03-16 | 4
Java backend setup | On Track |  |  | 2025-03-20 | 6
Web UI | On Track |  |  | 2025-03-26 | 7
Java UI | On Track |  |  | 2025-03-20 | 6
Database setup | On Track |  |  | 2025-03-26 | 7
Save client to DB | On Track |  |  | 2025-04-02 | 9
Save invoice to DB | On Track |  |  | 2025-04-02 | 9
Generate invoice PDF | On Track |  |  | 2025-04-02 | 9
Generate invoice PDF from DB | On Track |  |  | 2025-04-02 | 9
Testing & debugging | On Track |  |  | 2025-04-11 | 4
To add more data, Insert new rows ABOVE this one