## Sheet1
| Project Start Date: | 2025-02-26 |  | Feb |  | Mar | [9 empty] | Apr | [9 empty] | May
| Project Name: | Zero |  | 2025-02-26 | 2025-03-01 | 2025-03-04 | 2025-03-07 | 2025-03-10 | 2025-03-13 | 2025-03-16 | 2025-03-19 | 2025-03-22 | 2025-03-25 | 2025-03-28 | 2025-03-31 | 2025-04-03 | 2025-04-06 | 2025-04-09 | 2025-04-12 | 2025-04-15 | 2025-04-18 | 2025-04-21 | 2025-04-24 | 2025-04-27 | 2025-04-30 | 2025-05-03 | 2025-05-06 | 2025-05-09 | 2025-05-12 | 2025-05-15 | 2025-05-18 | 2025-05-21 | 2025-05-24 | 2025-05-27 | 2025-05-30
Task ID | Tasks | Assigned To | Status
0.1 | Finalizing project idea & tools | All | ✅ Completed | bar: 2025-02-26 to 2025-03-07
0.2 | Requirements + User stories | All | ✅ Completed | bar: 2025-03-10 to 2025-03-25
0.3 | Project planning + Task assignment | All | ✅ Completed | bar: 2025-03-25
0.4 | ERD + Schema Design | Emily, Tee, Sen | ✅ Completed | bar: 2025-03-25 to 2025-03-28
1.1 | Database Setup | Tee, Emily | ✅ Completed | bar: 2025-03-31
1.2 | Client management | Tee, Sen, Kevin | ✅ Completed | bar: 2025-04-03 to 2025-04-06
1.3 | Invoice System | Kevin, Tele | ✅ Completed | bar: 2025-03-25 to 2025-04-12
1.4 | Core Website Functionality | Tele, Sen, Kevin | ✅ Completed | bar: 2025-04-03 to 2025-04-15
2.1 | Bug Fixes | All | 🟡 In Progress | bar: 2025-04-09 to 2025-04-18
2.2 | Web UI Improvement | Emily, Kevin , Tele | 🟡 In Progress | bar: 2025-04-18
2.3 | Expense tracking feature | TBD | ⏳ Planned
2.4 | Financial statements (P/L, Balance Sheet) | TBD | ⏳ Planned
3.1 | Payroll automation | TBD | ⏳ Planned
3.2 | AI Financial Advice | TBD | ⏳ Planned
3.3 | Deployment | TBD | ⏳ Planned